AI SOLUTIONS BARBADOS

Production Launch Master Plan

Taking the AISB portfolio from demo to live — phased, tooled, executable.

At a Glance

Five phases. Estimated 10 weeks to first paying customer on the flagship and three more SaaS launches in market. Lead with AISB Invoicer (dogfood) and D's Nutz (engaged customer). Park Omniverce for capitalised-customer Phase 5.

Phase Overview

| Phase | Window | Outcome |
| --- | --- | --- |
| 0 — Commercial substrate | Week 1 | Legal, payments, hosting, support, secrets, domain all in place |
| 1 — Flagship: AISB Invoicer | Week 2-3 | Multi-tenant SaaS live; AISB billing through it; first external trial |
| 2 — D's Nutz Invoice→Journal | Week 4-5 | Second SaaS launch on the same multi-tenant skeleton |
| 3 — Fixed-price installs | Week 4-8 | Lieshua's, R.Ts, Sweetpea, Island Luxe, Eluvanaa, Great Kids — delivered + on retainer |
| 4 — Azure Gourmet chat | Week 6-10 | WhatsApp-verified multi-tenant chat backend live |
| 5 — Omniverce + future | Week 10+ | Park until a capitalised customer; reactivate from skeleton |

Tooling — Which Claude Surface Does What

| Surface | Best use in this rollout |
| --- | --- |
| Cowork (this surface) | Business docs, HTML apps, logos, screenshots, planning, training materials, customer-facing PDFs |
| Claude Code (CLI) | Multi-tenant refactor, backend code, deploys to Render/Vercel, Stripe SDK, GitHub, CI/CD, migrations |
| Claude in Chrome | SaaS dashboard work: Stripe, Cloudflare, Render, Meta Business Verification, QuickBooks consent |
| Claude in Excel | Customer pipeline tracker, hosting-cost spreadsheet, financial forecasts |
| MCP connectors | Direct action on Stripe/GitHub/Gmail/Slack once installed — reduces walk-throughs |

What I Will Do Per Phase

Phase 0 — Commercial substrate

Cowork: draft ToS, Privacy Policy, Service Agreement template (Barbados-tailored)

Cowork: draft customer onboarding checklist, subdomain strategy, founding customer pitch

Chrome: walk you through Stripe Atlas / standard signup

Chrome: set up support helpdesk (Help Scout free tier or Gmail label)

Chrome: configure Cloudflare DNS for aisolutionsbb.com subdomains

Chrome: set up Better Stack status page

Chrome: set up password vault (1Password / Bitwarden)

Claude Code (later in Phase 1): add /health endpoints + Sentry to all backends

Phase 1 — AISB Invoicer flagship

Claude Code: new repo, FastAPI/Next.js backend, tenant schema, auth, brand config

Claude Code: Stripe products + checkout + webhook handlers

Claude Code: deploy to Render with Postgres + custom domain invoices.aisolutionsbb.com

Cowork: signup-flow copy, trial→paid emails, marketing one-pager

Cowork: migration script for your existing localStorage invoices

Chrome: configure Render dashboard, Cloudflare DNS, Stripe products

Phase 2 — D's Nutz

Claude Code: multimodal pipeline (Gemini 2.5 Flash + image upload + JSON schema)

Claude Code: CSV/QuickBooks/Xero export adapters

Cowork: vendor list + chart-of-accounts template for D's Nutz

Cowork: training deck + cheat sheet for the 90-min onboarding session

Phase 3 — Fixed-price installs (per app)

Claude Code: final polish + bug pass in the existing repo

Claude Code: Vercel/Netlify deploy to customer subdomain

Chrome: DNS + hosting dashboard config

Cowork: training README/PDF + handover materials

Claude Code: Stripe recurring subscription for hosting retainer

Phase 4 — Azure Gourmet

Chrome: Meta Business Verification submission (start Phase 0 Day 1 — long lead)

Claude Code: multi-tenant chat backend refactor

Claude Code: WhatsApp webhook integration

Cowork: per-customer FAQ + catalog seeding template

Claude Code: per-tenant analytics dashboard

What You Have To Do (Cannot Be Delegated)

Add payment methods on every external service (Render, Vercel, Stripe, etc.)

Sign every contract — you are the legal entity

Have the actual customer conversations, demos, and training sessions

Make final pricing/business decisions when I escalate them to you

Approve schema and architecture choices before Claude Code commits code

Hold the master vault password — never share it, even with me

Risks and Honest Limits

Claude can write code faster than you can review it — your review bandwidth is the bottleneck, not my throughput

Meta WhatsApp verification takes 2–6 weeks with no AI shortcut — start it Day 1 of Phase 0

Eat your own invoicing in production for 2 weeks before billing the first external customer through it

Each MCP connector you install (Stripe, GitHub, Gmail) reduces the 'and-then-I-walk-you-through-the-UI' overhead. Install them aggressively as you go.

Customer onboarding has a human component AI cannot shortcut — 90 min per launch is real

Open Decisions Needed From You

| Question | Default if you don't answer |
| --- | --- |
| Flagship | Confirmed: AISB Invoicer (this doc assumes that) |
| Primary host | Render / Vercel / Railway — please pick. I recommend Render |
| Payment processor | Stripe vs WiPay/FirstCaribbean — Stripe recommended for global reach |
| On-call mode | DIY uptime, or paid Render Pro with managed support (~BBD $50/mo)? |
| Install-app repo ownership | AISB-owned with customer access, or transferred to customer at handover? |
| Founding pricing | 12-month locked rate, or 6-month then standard? |

AI Solutions Barbados · Jamai Puckerin · jp@aisolutionsbb.com